# MBS Road Control Tower

Knowledge Base · غرفة عمليات طريق الأمير محمد بن سلمان

Ministry of Municipalities & Housing

2026-05-19

Table of Contents

# MBS Road Control Tower — Knowledge Base

Curated reference for the MBS Road Control Tower Agent. Single source of truth for leadership briefings, agent onboarding, and LLM context.

Corridor: Prince Mohammed bin Salman Road · Jeddah → Makkah · 75 km · 170,000+ vehicles/day Owner: Saudi Ministry of Municipalities & Housing (MoMAH) Document version: 0.1 · synthetic PoC data (Zones 8, 35, 70 only)

## Table of contents

| # | Section | What’s inside |
| --- | --- | --- |
| 00 | Executive Summary | 1-page leadership view: corridor, KPIs, Hajj readiness, top risks |
| 01 | Corridor Overview | The 75 km road, 3 sub-stretches, 5 phases, the strategic case |
| 02 | 2027 Targets (KPIs) | All 6 KPIs with current %, target %, weekly trend, status |
| 03 | Zones — PoC Detail | Full picture of Zones 8, 35, 70 — findings, budgets, assets, contractors |
| 04 | Contractors & Governance | The 10 contractors, why governance is a root cause, joint-room proposal |
| 05 | Activity Types & Glossary | Development vs Operational, distortion categories, key terms |
| 06 | Questions & Answers | 54 bilingual (EN+AR) Q&A pairs grouped by topic |
| 07 | Facts Snapshot (JSON) | Machine-readable single source of truth — feeds the LLM |

## How to use this folder

| Audience | Read first |
| --- | --- |
| Leadership briefing | 00-executive-summary.md |
| Stakeholder review | 01-corridor-overview.md → 02-2027-targets.md → 04-contractors-and-governance.md |
| Agent / LLM training | 06-questions-and-answers.md + 07-facts-snapshot.json |
| Field / operational team | 03-zones.md + 05-activity-types-and-glossary.md |

## Snapshot at a glance

| Metric | Value |
| --- | --- |
| Corridor length | 75 km |
| Daily vehicles | 170,000+ |
| Zones | 75 (1 km each) |
| Operational phases | 5 (15 zones each) |
| Geographic sub-stretches | 3 (Port · Middle · Haram) |
| Contractors involved | 10 |
| 2027 KPIs tracked | 6 |
| PoC zones with synthetic data | Z8, Z35, Z70 |
| Findings tracked (PoC) | 26 (10 Development · 16 Operational) |
| Q&A pairs in the KB | 62 (bilingual EN/AR · incl. vendor performance) |

## Sources

- April 2026 report — Status of Prince Mohammed bin Salman Road Axis in the Makkah region and proposed remediation actions (Saudi Ministry of Municipalities & Housing)

- PoC synthetic data — generated to demonstrate the platform pending live data integration

Document classification: internal MoMAH briefing material · synthetic PoC data

# 00 · Executive Summary

For: MoMAH leadership About: Status of the Prince Mohammed bin Salman Road Axis (Jeddah → Makkah)

## The corridor in one line

A 75 km strategic link between Jeddah Islamic Port and Al-Masjid Al-Haram, carrying 170,000+ vehicles daily — the principal road for pilgrims, Umrah travellers, logistics flows, and inter-city commerce.

## Why the program exists

The April 2026 ministerial report identified four root-cause challenges along the corridor:

- No single supervising authority — work is split across 7 contractors with overlapping mandates

- Visual distortion (تشوه بصري) — slums, illegal workshops, code-violating fuel stations, damaged ad boards, deteriorated asphalt

- Weak infrastructure — barriers, bridge perimeters, asphalt, inspection-point quality

- Unused economic opportunity — vacant municipal land, untapped advertising/concession potential

## 2027 targets — current status

| KPI | Target | Today | Weekly Δ | On track? |
| --- | --- | --- | --- | --- |
| Road maintenance coverage | 100% | 38% | +4.2% | ✓ |
| Buildings compliant with urban codes | 70% | 22% | +2.1% | ✗ |
| Illegal workshops & yards cleared | 100% | 41% | +6.0% | ✗ (but strongest weekly gain) |
| Damaged concrete barriers repaired | 90% | 53% | +5.3% | ✓ |
| Condemned buildings demolished | 100% | 28% | +3.7% | ✗ |
| Greenery & median planting added | 100% | 19% | +1.4% | ✗ (slowest) |

## Hajj readiness

- Next Hajj target date: 2027-05-25

- Overall corridor is tracking but behind the ramp on 4 of 6 KPIs

- Highest priority zone: Z70 (Prince Nayef → Holy Mosque approach) — direct pilgrim entry

## Top risks (synthesized from PoC findings)

- Greenery uplift is the slowest-moving KPI (+1.4% / wk vs. 100% target). Without acceleration, the visual welcome experience for pilgrims will lag.

- Building compliance is at 22% of a 70% target with only +2.1% weekly momentum.

- Repeat-offender pattern: workshops in Z8 have been flagged for the 3rd time in the quarter (oil spills). Operational handling is no longer sufficient — needs a development-level intervention (licensing review or demolition).

- Inter-contractor hand-offs: blocked items concentrated in items requiring coordination between RGA (roads) and the municipalities (HCM/JM).

## Proposed governance fix

An independent program led by MoMAH that combines the Holy Capital Municipality (Makkah) and Jeddah Municipality in a joint working room with formal authority over findings remediation and stakeholder coordination.

→ Continue to 01 · Corridor Overview

# 01 · Corridor Overview

## The road

| Official name | Prince Mohammed bin Salman Road Axis (محور طريق الأمير محمد بن سلمان) |
| --- | --- |
| Region | Makkah, Saudi Arabia |
| Length | 75 km |
| Endpoints | Jeddah Islamic Port → Al-Masjid Al-Haram |
| Daily traffic | 170,000+ vehicles |
| Primary user mix | Pilgrims & Umrah travellers, inter-city commuters, logistics, recreational, diplomatic |

## Strategic importance

The corridor is the principal vehicle link between Jeddah and Makkah and the main road by which pilgrims, Umrah travellers, and diplomatic guests reach Al-Masjid Al-Haram. It is also a critical logistics spine from the Islamic Port — so visual quality, traffic flow, and safety along it carry outsized symbolic and operational weight for the Kingdom.

## The 3 geographic sub-stretches

The corridor splits naturally into three contexts:

0 km            30 km                   64 km    75 km
●──────────────────●──────────────────────────●────────●
Jeddah Port     Bahrah Bridge        Prince Nayef    Holy Mosque
   │                  │                     │            │
   └─── PORT ─────────┴────── MIDDLE ────────┴── HARAM ──┘
       (30 km)              (34 km)             (11 km)

| ID | Stretch | Length | Character |
| --- | --- | --- | --- |
| port | Port → Bahrah | 0 – 30 km | Logistics & port traffic, workshops, mechanic yards, heavy vehicles |
| middle | Bahrah → Prince Nayef | 30 – 64 km | Inter-city movement, fuel stations, ad boards, slum pockets |
| haram | Prince Nayef → Holy Mosque | 64 – 75 km | Pilgrim approach — highest leadership scrutiny, visual welcome critical |

## The 5 operational phases × 15 zones

Independent of geography, the corridor is divided into 75 zones of 1 km each, grouped into 5 rollout phases of 15 zones. Every zone carries both a phase (when work is scheduled) and a sub-stretch (its geographic character).

| Phase | Zones | Notes |
| --- | --- | --- |
| 1 | Z1 – Z15 | Port-side launch (starts logistics belt) |
| 2 | Z16 – Z30 | Crosses into Bahrah |
| 3 | Z31 – Z45 | Middle stretch — slum + ad-board concentration |
| 4 | Z46 – Z60 | Toward Prince Nayef |
| 5 | Z61 – Z75 | Haram approach — Hajj-readiness priority |

## Distortion density (3-band classification)

Each zone is rated on a 3-band scale of visible distortion concentration:

| Band | Color (UI) | Meaning |
| --- | --- | --- |
| Low | 🟢 Green | Few or no distortion items; mostly compliant |
| Medium | 🟠 Orange | Some clusters of distortion; needs scheduled attention |
| High | 🔴 Red | Dense clusters; priority for development / remediation |

Concentration belts (high density): workshops around Z8–Z14, slums and ad-boards around Z33–Z40, fuel-station & barrier issues around Z50–Z56, pilgrim-approach issues around Z66–Z72.

## PoC scope

Synthetic data is currently populated for three zones — one per sub-stretch:

- Z8 — Port stretch · Phase 1 · workshops & barriers

- Z35 — Middle stretch · Phase 3 · slums, ad boards, fuel stations

- Z70 — Haram approach · Phase 5 · bridge perimeter & inspection point

→ Continue to 02 · 2027 Targets (KPIs)

# 02 · 2027 Targets (KPIs)

Source: Slide 11 of the April 2026 MoMAH report — Outcomes targeted by end of 2027 Numbers below: synthetic PoC values reflecting the kind of leadership KPI panel that will be hydrated with live operational data.

## Snapshot

| # | KPI | Target | Today | Weekly Δ | On track? |
| --- | --- | --- | --- | --- | --- |
| 1 | Road maintenance coverage | 100% | 38% | +4.2% | ✓ |
| 2 | Buildings compliant with urban codes | 70% | 22% | +2.1% | ✗ |
| 3 | Illegal workshops & yards cleared | 100% | 41% | +6.0% | ✗ |
| 4 | Damaged concrete barriers repaired | 90% | 53% | +5.3% | ✓ |
| 5 | Condemned buildings demolished | 100% | 28% | +3.7% | ✗ |
| 6 | Greenery & median planting added | 100% | 19% | +1.4% | ✗ |

On-track rule: current % is at least 50% of its target % at the current point in the program.

## 1. Road maintenance coverage

Target: 100% of the corridor under active maintenance coverage by end of 2027. Today: 38% · trending +4.2% / week

Maintenance coverage = asphalt overlay, drainage, signage, line-painting, joint-sealing across the 75 km. This is the flagship 100%-by-2027 commitment and the most visible signal that the corridor is being looked after.

## 2. Buildings compliant with urban codes

Target: 70% of corridor-facing buildings compliant with the unified urban code by end of 2027. Today: 22% · trending +2.1% / week

Compliance covers façade design, height, signage size, setbacks, materials. Lifting this number requires sustained pressure on building owners — currently the slowest-moving “code” KPI.

## 3. Illegal workshops & yards cleared

Target: 100% of unlicensed mechanic / bodywork / warehouse operations cleared from the right-of-way and adjacent strip by end of 2027. Today: 41% · trending +6.0% / week — the strongest weekly delta.

Driven mostly by Z8-style port-stretch clearances. The trend suggests this KPI hits target ahead of plan if pace is sustained.

## 4. Damaged concrete barriers repaired

Target: 90% of damaged median and edge barriers repaired or replaced by end of 2027. Today: 53% · trending +5.3% / week — the leading on-track indicator (highest ratio of current to target).

## 5. Condemned buildings demolished

Target: 100% of buildings with cancelled title deeds (مباني ملغاة صكوكها) demolished by end of 2027. Today: 28% · trending +3.7% / week

Linked to slum-area work in Z35. Most of the slowdown is process — coordination with social services for resident relocation before demolition.

## 6. Greenery & median planting added

Target: 100% of the planned greenery & median planting installed by end of 2027. Today: 19% · trending +1.4% / week — the furthest behind.

This is the visual-welcome KPI for pilgrims. The pace needs to roughly double to make Hajj 2027.

## What leadership should watch

| Watch | Why |
| --- | --- |
| Greenery acceleration plan | Lowest weekly velocity (+1.4%) against a 100% target. Without intervention, visual welcome experience for Hajj 2027 will lag. |
| Compliance enforcement cadence | Building code compliance moves at +2.1%/wk; 70% target may slip. |
| Demolition coordination | Condemned-building demolitions are bottlenecked by social-services relocation timing. |
| Workshop clearance momentum | Strongest mover at +6.0%/wk — protect this pace; lock in contractor capacity. |

→ Continue to 03 · Zones — PoC Detail

# 03 · Zones — PoC Detail

Detailed picture of the three PoC zones (one per geographic sub-stretch). Each contains the corridor’s characteristic challenges in microcosm.

| Zone | Phase | Sub-stretch | km range | Density | Daily traffic | Findings | Open |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Z8 | 1 | Port | 7 – 8 | High | ~96,000 | 8 | 5 |
| Z35 | 3 | Middle | 34 – 35 | High | ~134,000 | 9 | 6 |
| Z70 | 5 | Haram | 69 – 70 | High | ~178,000 | 9 | 4 |

## Zone 8 — Port stretch

Phase 1 · port sub-stretch · workshops belt

The first concentration of distortion on the corridor. Mechanic and bodywork shops have grown organically along the right-of-way, with heavy-vehicle traffic deteriorating the asphalt and median barriers.

### Findings

| ID | Type | Title | Status | Severity | Owner |
| --- | --- | --- | --- | --- | --- |
| F-Z8-001 | Dev | Demolish 14 unlicensed workshops north of carriageway | In progress | High | JM |
| F-Z8-002 | Dev | Replace 1.2 km of damaged concrete barriers (median) | Open | High | RGA |
| F-Z8-003 | Dev | Overlay 1.0 km asphalt — eastbound lanes | Done | Medium | RGA |
| F-Z8-004 | Ops | Remove 6 non-compliant ad boards | In progress | Medium | JM |
| F-Z8-005 | Ops | Fuel station signage code violation — Station #12 | Open | Low | JM |
| F-Z8-006 | Ops | Open trench left unfilled by utility contractor | Blocked | High | RGA |
| F-Z8-007 | Ops | Recurring oil-spill from car repair yard (×3) | In progress | High | GDCD |
| F-Z8-008 | Dev | Plant 320 native trees along north service road | Open | Low | Investment |

Budget: SAR 15,450,000 committed · SAR 4,990,000 spent (~32%)

### Assets in zone

- Logistics Service Center

- Fuel Station #12 (under signage review)

- Inspection Point — Port

### What leadership should know

- Z8-007 is a repeat-offender pattern (3rd flag this quarter) — operational remediation is no longer working; needs a development-level decision (licensing review or demolition).

- Z8-006 is blocked by a non-responsive fiber contractor — escalation candidate for the joint working room.

## Zone 35 — Middle stretch

Phase 3 · middle sub-stretch · slums, ad boards, fuel stations

The corridor’s most visually disorderly stretch: a residential slum cluster south of the carriageway, a chain of oversize / mis-sized ad boards, and a fuel-station plaza non-compliant with the new urban code.

### Findings

| ID | Type | Title | Status | Severity | Owner |
| --- | --- | --- | --- | --- | --- |
| F-Z35-001 | Dev | Demolish slum area (≈42 condemned dwellings) | In progress | High | HCM |
| F-Z35-002 | Dev | Re-tender ad-board concession (visual-quality plan) | Open | Medium | Investment |
| F-Z35-003 | Dev | Rebuild Service Plaza #4 to new urban code | Open | Medium | Investment |
| F-Z35-004 | Ops | Daily refuse pile-up at slum boundary | In progress | Medium | HCM |
| F-Z35-005 | Ops | Two ad boards leaning post-windstorm | Done | High | HCM |
| F-Z35-006 | Ops | Canopy paint faded — Station #18 | Open | Low | HCM |
| F-Z35-007 | Ops | Building façade graffiti (3 buildings) | In progress | Low | HCM |
| F-Z35-008 | Ops | Pothole cluster — westbound shoulder | Open | Medium | RGA |
| F-Z35-009 | Dev | Convert 6 ha of vacant median to landscaped strip | Open | Low | Investment |

Budget: SAR 31,200,000 committed · SAR 4,200,000 spent (~13%)

### Assets in zone

- Condemned dwellings cluster (slum boundary, in demolition)

- Service Plaza #4 (under rebuild)

- Median landscaping strip (planned)

### What leadership should know

- Largest development budget of any PoC zone (SAR 31.2M), but only 13% spent — most work is at procurement / pre-mobilization stage.

- The slum demolition (F-Z35-001) is the corridor’s most stakeholder-sensitive item: requires coordinated relocation with social services.

- HCM owns most of this zone’s items (6 of 9) — clear single-contractor accountability.

## Zone 70 — Haram approach

Phase 5 · haram sub-stretch · pilgrim entry

The most leadership-visible zone on the corridor. Welcomes pilgrims at Prince Nayef Bridge with the bridge perimeter, inspection point, and final median planting setting the first impression of the Makkah experience.

### Findings

| ID | Type | Title | Status | Severity | Owner |
| --- | --- | --- | --- | --- | --- |
| F-Z70-001 | Dev | Restore Prince Nayef Bridge approach perimeter | In progress | High | RGA |
| F-Z70-002 | Dev | Replace inspection-point canopy & paint | Open | High | GDT |
| F-Z70-003 | Dev | Replace 600 m concrete barriers — bridge approach | In progress | High | RGA |
| F-Z70-004 | Ops | Trash overflow at inspection point | In progress | Medium | HCM |
| F-Z70-005 | Ops | Unauthorized vinyl banner on overpass railing | Open | Low | HCM |
| F-Z70-006 | Ops | Reflective paint worn on 80 m of barriers | Open | Medium | RGA |
| F-Z70-007 | Ops | Surface cracking — bridge expansion joint | In progress | High | RGA |
| F-Z70-008 | Dev | Pilgrim approach landscaping — median planting | Open | Medium | Investment |
| F-Z70-009 | Ops | Adjacent building façade obstructing welcome signage | Blocked | Medium | HCM |

Budget: SAR 20,750,000 committed · SAR 5,120,000 spent (~25%)

### Assets in zone

- Prince Nayef Bridge — approach (under perimeter restoration)

- Pilgrim-Approach Inspection Point

- Welcome landscaping median (planned)

### What leadership should know

- 4 of 9 findings are high severity — the densest high-severity concentration of any PoC zone.

- Z70-009 is blocked waiting on a building owner to remove a façade obstruction — escalation candidate.

- Three high-severity development items (bridge perimeter, inspection canopy, barrier replacement) must close before Hajj 2027 to deliver the welcome experience.

## Cross-zone summary

| Metric | Z8 | Z35 | Z70 | Total |
| --- | --- | --- | --- | --- |
| Findings | 8 | 9 | 9 | 26 |
| Development | 3 | 4 | 3 | 10 |
| Operational | 5 | 5 | 6 | 16 |
| Open | 5 | 6 | 4 | 15 |
| Done | 1 | 1 | 0 | 2 |
| Blocked | 1 | 0 | 1 | 2 |
| High severity | 4 | 1 | 4 | 9 |
| Budget committed (SAR) | 15.45 M | 31.20 M | 20.75 M | 67.40 M |
| Budget spent (SAR) | 4.99 M | 4.20 M | 5.12 M | 14.31 M |

→ Continue to 04 · Contractors & Governance

# 04 · Contractors & Governance

Why this matters: The April 2026 report names lack of a single supervising authority as the first of four root-cause challenges. The corridor is delivered by 10 contractors — 6 government-internal teams and 4 private-sector vendors — and leadership needs a single view of who is performing, who is slipping, and who needs intervention.

## The 10 contractors

| Acronym | Full name (EN) | Full name (AR) | Kind | Scope |
| --- | --- | --- | --- | --- |
| MoMAH | Ministry of Municipalities & Housing | وزارة البلديات والإسكان | Government | Governance owner, standards, policy |
| HCM | Holy Capital Municipality (Makkah) | أمانة العاصمة المقدسة | Government | Operates the Makkah-side stretch (in-house) |
| JM | Jeddah Municipality | أمانة جدة | Government | Operates the Jeddah-side stretch (in-house) |
| RGA | Roads General Authority | الهيئة العامة للطرق | Government | Asphalt, bridges, road safety (internal program) |
| GDT | General Department of Traffic | الإدارة العامة للمرور | Government | Traffic flow, inspection points |
| GDCD | General Directorate of Civil Defense | المديرية العامة للدفاع المدني | Government | Emergency, safety inspections |
| ARC | Al-Rajhi Construction Co. | شركة الراجحي للإنشاءات | Private | Heavy civil works — demolition, asphalt, barriers |
| SBG | Saudi Binladin Group | مجموعة بن لادن السعودية | Private | Bridge restoration, structural & pilgrim-approach |
| MAAS | MA’AS Services | ماس للخدمات | Private | Daily ops — refuse, signage, graffiti, ad-board take-downs |
| TIP | Tatweer Investment Partner | شريك تطوير الاستثمار | Private (PPP) | Ad-board concessions, fuel-station rebuild, greenery |

## Vendor Scorecard

Synthetic PoC data — designed to demonstrate the kind of vendor oversight leadership needs.

| Contractor | Contract value (SAR) | On-time % | Quality | Fines YTD (SAR) | Late items | Escalations |
| --- | --- | --- | --- | --- | --- | --- |
| MAAS | 8.5 M | 94% | 88 | 25,000 | 0 | 0 |
| HCM | 9.4 M | 81% | 82 | 0 | 1 | 1 |
| JM | 6.2 M | 76% | 79 | 0 | 1 | 0 |
| GDT | 1.75 M | 70% | 84 | 0 | 1 | 0 |
| SBG | 14.8 M | 71% | 92 | 180,000 | 1 | 1 |
| ARC | 22.5 M | 64% | 73 | 450,000 | 2 | 2 |
| RGA | 11.8 M | 58% | 78 | 0 | 3 | 2 |
| TIP | 18.9 M | 52% | 76 | 320,000 | 3 | 1 |
| GDCD | 0 | 100% | 95 | 0 | 0 | 0 |
| MoMAH | 0 | 100% | 100 | 0 | 0 | 0 |

Total corridor contract value committed: ~ SAR 93.8 M across all contractors.

### What the scorecard shows

| Signal | What we see |
| --- | --- |
| Best operational performer | MAAS — 94% on-time, near-zero fines. Protect this contract. |
| Highest quality | SBG — 92/100 quality (best bridge work). Trade-off: slower delivery. |
| Most concerning | TIP — only 52% on-time, SAR 320k fines, 3 late items on a SAR 18.9 M contract. |
| Most fined | ARC — SAR 450k YTD. Big contract value (22.5 M) but discipline issues. |
| Quietly slipping | RGA — internal team running 3 late items on barrier replacement. |

## Why governance is a root cause

Per the report (slide 9), corridor work today touches:

- 4 contractors in maintenance

- 7 contractors in infrastructure projects

- 3 contractors in studies

- 4 contractors (incl. private sector) in commercial / concession projects

This fragmentation creates predictable failure modes:

- No single owner for end-to-end outcomes. Pilgrim-experience targets like “the corridor is clean and welcoming for Hajj” fall between RGA (road), HCM (street), GDT (traffic posts), and TIP (greenery). When something slips, accountability diffuses.

- Coordination tax on every multi-contractor item. F-Z70-009 (façade obstructing welcome signage) is blocked because the fix requires HCM enforcement, owner notice, and possibly RGA/GDT sign-off.

- Duplicated studies, inconsistent standards. Different contractors commission separate studies for adjacent assets, producing incompatible specs.

- No unified operational view. Leadership cannot ask “what is the status of MBS Road this week — including vendor performance?” and get one answer.

## The proposed fix — Joint Working Room

The report recommends standing up an independent program with three properties:

| Property | Detail |
| --- | --- |
| Lead | MoMAH (single accountable owner) |
| Members | HCM (Makkah side) + JM (Jeddah side), plus standing seats for RGA, GDT, GDCD, and the private contractors (ARC, SBG, MAAS, TIP) |
| Mandate | Authority over findings remediation, contractor performance review, contractor escalation, single weekly status report to leadership |

Operating model: weekly cadence, shared findings backlog, vendor scorecard reviewed monthly, escalation SLA for blocked items (target: any blocked item resolved in the room ≤ 10 days).

## Implication for the agent

The agent must:

- Speak in the language of the joint room, not in contractor silos

- For every finding, surface the executing contractor alongside status and severity (so leadership knows whom to call)

- Highlight blocked items where the blocker is a contractor hand-off (these are exactly what the room exists to resolve)

- Flag vendors with deteriorating performance before they become escalations

→ Continue to 05 · Activity Types & Glossary

# 05 · Activity Types & Glossary

## The two activity types

The corridor’s work is organized into two distinct activity types with different lifecycles, owners, and budgets.

|  | Development Activity | Operational Activity |
| --- | --- | --- |
| Source | The report’s 4 root-cause findings | Day-to-day inspector findings |
| Cycle | Long (months to years) | Short (days to weeks) |
| Owner type | Capital-project teams + contractors | Field inspectors + cleaning / maintenance crews |
| Budget | Significant (SAR millions) | Operational ledger (no per-item budget) |
| Examples | New fuel station to code · workshop demolition · barrier replacement · asphalt overlay · bridge restoration · greenery program | Ad-board removal · graffiti cleanup · pothole patch · refuse collection · faded paint · signage fix |
| Lifecycle | Plan → Tender → Mobilize → Construct → Handover | Open → Assigned → Fixed → Verified |
| Linked to | Concrete capital project IDs | An inspector name + a reopened-count metric |

In the corridor today: 10 Development items + 16 Operational items across the 3 PoC zones (26 total).

## When operational findings escalate to development

A repeat-offender pattern signals that operational handling is insufficient. The threshold pattern:

Same finding category, same location, reopen count > 2 → escalate to a development decision (licensing review, demolition, code-level change).

Example in PoC scope: F-Z8-007 (recurring oil-spill from a car repair yard) has reopened 3 times this quarter. The next ticket type is a development item — licensing review or workshop demolition.

## Distortion categories (10)

The 10 distortion manifestations identified in the report (slide 6). Each finding is tagged with one.

| Category (EN) | Category (AR) | Typical owner |
| --- | --- | --- |
| Slums | عشوائيات | HCM / JM |
| Buildings violating urban codes | مباني غير ملتزمة بالأكواد | HCM / JM |
| Damaged concrete barriers | تشوه الحواجز الخرسانية | RGA |
| Asphalt deterioration / open trenches | تدهور الأرصفة / حفر | RGA |
| Bridge perimeter degradation | تدهور حرم الجسور | RGA |
| Fuel / service-station code violations | عدم التزام محطات الوقود | HCM / JM / Investment |
| Distorted ad boards | لوحات إعلانية مشوهة | HCM / JM / Investment |
| Unfinished construction (سواكر) | سواكر | HCM / JM |
| Illegal workshops & warehouses | ورش ومستودعات غير نظامية | JM / GDCD |
| Inspection-point appearance | مظهر نقاط التفتيش | GDT / HCM |

## Asset types (mapped on the corridor)

| Asset (EN) | Asset (AR) | Notes |
| --- | --- | --- |
| Bridge | كبري | e.g., Prince Nayef Bridge (Z70), Bahrah Bridge |
| Fuel station | محطة وقود | Code compliance is a recurring issue |
| Inspection point | نقطة تفتيش | GDT-operated, appearance matters for pilgrim welcome |
| Service center | مركز خدمات | Logistics / commercial cluster |
| Slum area | عشوائيات | Demolition + relocation lifecycle |
| Greenery / median strip | تشجير / جزر وسطية | The slowest-moving 2027 KPI |

## Glossary

| Term (EN) | Term (AR) | Definition |
| --- | --- | --- |
| Visual / urban distortion | تشوه بصري / حضري | Any element that degrades the visual quality of the corridor — graffiti, oversize ad boards, unfinished construction, abandoned vehicles, broken barriers, etc. |
| Zone | نطاق | A 1-km segment of the corridor. There are 75 zones in total (Z1–Z75). PoC data exists for Z8, Z35, Z70. |
| Phase | مرحلة | One of 5 operational rollout phases. Each phase covers 15 zones (15 km). |
| Sub-stretch | قطاع جغرافي | One of three natural geographic segments: Port (0–30 km), Middle (30–64 km), Haram (64–75 km). |
| Development activity | نشاط تطويري | Major capital fix — has budget, contractor, target date. |
| Operational activity | نشاط تشغيلي | Day-to-day inspector finding — short cycle, no major budget. |
| Repeat offender | مخالف متكرر | A property / asset flagged for the same finding ≥ 3 times — triggers escalation. |
| Blocked | متعثرة | Work that cannot progress because of an external dependency. The joint working room’s first-priority queue. |
| Joint working room | غرفة عمل مشتركة | The proposed multi-contractor operations room led by MoMAH (with HCM + JM as core members). |
| Hajj-readiness | جاهزية الحج | Cumulative progress on visible items along the pilgrim approach, anchored to the next Hajj date. |
| PoC zone | نطاق تجريبي | One of {Z8, Z35, Z70} — zones populated with synthetic data for this proof of concept. |

→ Continue to 06 · Questions & Answers

# 06 · Questions & Answers

62 bilingual (EN+AR) Q&A pairs the MBS Road Control Tower Agent must answer reliably. Each answer is grounded in the Facts Snapshot — the agent never invents numbers.

## Index

| # | Category | Questions |
| --- | --- | --- |
| 01 | Corridor basics | 4 |
| 02 | Phases & zones | 5 |
| 03 | 2027 targets / KPIs | 8 |
| 04 | Findings — status | 8 |
| 05 | Findings — by zone | 8 |
| 06 | Contractors & governance | 6 |
| 07 | Vendor performance | 8 |
| 08 | Budget | 4 |
| 09 | Hajj readiness | 4 |
| 10 | Activity types | 4 |
| 11 | Scope & safety | 3 |

## 1. Corridor basics

أساسيات المحور

### C-01 How long is the MBS Road corridor and where does it run?

ما طول محور طريق الأمير محمد بن سلمان وأين يمتد؟

Answer (EN): 75 km from Jeddah Islamic Port to Al-Masjid Al-Haram in Makkah.

Answer (AR): 75 كم من ميناء جدة الإسلامي إلى المسجد الحرام في مكة المكرمة.

### C-02 How many vehicles use the road every day?

كم عدد المركبات التي تستخدم الطريق يومياً؟

Answer (EN): More than 170,000 vehicles daily.

Answer (AR): أكثر من 170,000 مركبة يومياً.

### C-03 Why is this corridor strategically important?

لماذا يُعد هذا المحور استراتيجياً؟

Answer (EN): It is the principal connection between Jeddah and Makkah and the main road used by pilgrims and Umrah travellers to reach Al-Masjid Al-Haram, as well as a logistics spine from the Islamic Port.

Answer (AR): يمثل الرابط الرئيسي بين جدة ومكة والطريق الأساسي الذي يستخدمه الحجاج والمعتمرون للوصول إلى المسجد الحرام، فضلاً عن كونه عموداً فقرياً للوجستيات من الميناء الإسلامي.

### C-04 What are the three geographic sub-stretches of the road?

ما القطاعات الجغرافية الثلاثة للطريق؟

Answer (EN): Port → Bahrah (0–30 km, logistics & workshops), Bahrah → Prince Nayef (30–64 km, inter-city / fuel / ad-boards / slum pockets), and Prince Nayef → Holy Mosque (64–75 km, pilgrim approach).

Answer (AR): الميناء → بحرة (0–30 كم، لوجستيات وورش)، بحرة → الأمير نايف (30–64 كم، نقل بين مدن / محطات وقود / لوحات / عشوائيات)، الأمير نايف → الحرم (64–75 كم، مدخل الحجاج).

## 2. Phases & zones

المراحل والنطاقات

### S-01 How is the corridor broken down into phases and zones?

كيف يُقسَّم المحور إلى مراحل ونطاقات؟

Answer (EN): 5 rollout phases, each covering 15 zones of 1 km — 75 zones in total. Phase 1: Z1–Z15, Phase 2: Z16–Z30, Phase 3: Z31–Z45, Phase 4: Z46–Z60, Phase 5: Z61–Z75.

Answer (AR): 5 مراحل إطلاق، كل واحدة تغطي 15 نطاقاً من كم — إجمالي 75 نطاقاً. المرحلة 1: Z1–Z15، المرحلة 2: Z16–Z30، المرحلة 3: Z31–Z45، المرحلة 4: Z46–Z60، المرحلة 5: Z61–Z75.

### S-02 Which zones are part of the proof-of-concept?

ما النطاقات المشمولة في المرحلة التجريبية؟

Answer (EN): Three zones: Z8 (port stretch — workshops belt), Z35 (middle stretch — slum + ad-board cluster), Z70 (Haram approach — bridge perimeter & pilgrim entry).

Answer (AR): ثلاثة نطاقات: Z8 (قطاع الميناء — حزام ورش)، Z35 (القطاع الأوسط — عشوائيات ولوحات)، Z70 (مدخل الحرم — حرم الكبري ومدخل الحجاج).

### S-03 What is the difference between a phase and a sub-stretch?

ما الفرق بين المرحلة والقطاع الجغرافي؟

Answer (EN): A phase is an operational rollout slice (when work is scheduled). A sub-stretch is a geographic character (port-logistics vs middle vs Haram approach). Every zone carries both labels.

Answer (AR): المرحلة شريحة إطلاق تشغيلية (متى سيُنفَّذ العمل). القطاع الجغرافي يصف طبيعة الموقع (ميناء ولوجستيات / وسط / مدخل الحرم). كل نطاق يحمل التصنيفين معاً.

### S-04 Which phase does Zone 70 belong to?

إلى أي مرحلة ينتمي النطاق 70؟

Answer (EN): Phase 5 (Z61–Z75), sub-stretch ‘Prince Nayef → Holy Mosque’.

Answer (AR): المرحلة 5 (Z61–Z75)، القطاع ‘الأمير نايف → الحرم’.

### S-05 What distortion-density bands are used on the map?

ما تصنيفات كثافة التشوه المستخدمة على الخريطة؟

Answer (EN): Three: low (green), medium (orange), high (red). Each 1 km zone is colored by its current band.

Answer (AR): ثلاثة: منخفضة (أخضر)، متوسطة (برتقالي)، عالية (أحمر). كل نطاق طوله 1 كم يُلوّن بحسب تصنيفه الحالي.

## 3. 2027 targets / KPIs

مستهدفات 2027

### K-01 How many 2027 targets are we tracking?

كم عدد مستهدفات 2027 التي نتابعها؟

Answer (EN): Six: road maintenance coverage, building compliance, illegal-workshop removal, barrier repair, condemned-building demolition, greenery & median planting.

Answer (AR): ستة: تغطية الصيانة، امتثال المباني، إزالة الورش غير النظامية، إصلاح الحواجز، هدم المباني الملغاة، التشجير والجزر الوسطية.

### K-02 What is the road-maintenance coverage target and where are we?

ما مستهدف تغطية صيانة الطريق وأين وصلنا؟

Answer (EN): Target is 100% coverage by end of 2027. We are at 38% currently, trending +4.2% per week.

Answer (AR): المستهدف 100% تغطية بحلول نهاية 2027. الوضع الحالي 38%، باتجاه +4.2% أسبوعياً.

### K-03 How are we doing on barrier-repair progress?

ما تقدّمنا في إصلاح الحواجز الخرسانية؟

Answer (EN): Target: 90% repaired by 2027 end. Current: 53% (+5.3% weekly).

Answer (AR): المستهدف: إصلاح 90% بنهاية 2027. الحالي: 53% (+5.3% أسبوعياً).

### K-04 Which KPI is furthest behind?

أي مستهدف هو الأكثر تأخراً؟

Answer (EN): Greenery & median planting — only 19% of the 100% target so far, growing slowly at +1.4% per week.

Answer (AR): التشجير والجزر الوسطية — 19% فقط من المستهدف 100%، ينمو ببطء بمعدل +1.4% أسبوعياً.

### K-05 Which KPI is most on track?

أي مستهدف هو الأقرب للمسار المخطط؟

Answer (EN): Damaged-barrier repair — 53% of a 90% target (≈59% of target) — the leading indicator.

Answer (AR): إصلاح الحواجز — 53% من مستهدف 90% (≈59% من المستهدف) — أعلى نسبة تحقيق.

### K-06 What is the building-compliance target?

ما مستهدف امتثال المباني؟

Answer (EN): 70% of buildings on the corridor compliant with the unified urban code by 2027 end. Currently at 22% (+2.1% weekly).

Answer (AR): 70% من المباني على المحور ممتثلة للكود العمراني الموحد بنهاية 2027. الحالي 22% (+2.1% أسبوعياً).

### K-07 How many condemned buildings still need to be demolished?

كم مبنى ملغى الصك ما زال يحتاج للهدم؟

Answer (EN): We are at 28% of the 100% demolition target — about 72 percentage points remaining (proportional to the corridor’s total condemned-building inventory).

Answer (AR): وصلنا إلى 28% من مستهدف الهدم البالغ 100% — يتبقى نحو 72 نقطة مئوية (متناسبة مع مجموع المباني الملغاة على المحور).

### K-08 What is the workshop-clearance target?

ما مستهدف إزالة الورش غير النظامية؟

Answer (EN): 100% of illegal workshops & warehouses cleared by 2027 end. At 41% so far, +6.0% per week — strongest weekly delta.

Answer (AR): إزالة 100% من الورش والمستودعات غير النظامية بنهاية 2027. الحالي 41%، +6.0% أسبوعياً — أعلى نسبة تغيّر أسبوعي.

## 4. Findings — status

الملاحظات — الحالة

### F-01 How many open findings are there in the PoC scope?

كم عدد الملاحظات المفتوحة ضمن نطاق التجربة؟

Answer (EN): Refer to findings_aggregate.open + in_progress + blocked counts.

Answer (AR): يُرجى الاطلاع على إجمالي findings_aggregate.open + in_progress + blocked.

### F-02 What is our overall closure rate?

ما معدل الإغلاق الإجمالي؟

Answer (EN): Computed as done / total. See findings_aggregate.done and findings_aggregate.total.

Answer (AR): يُحسب بـ done / total. انظر findings_aggregate.done و findings_aggregate.total.

### F-03 How many findings are currently blocked?

كم ملاحظة متعثرة حالياً؟

Answer (EN): See findings_aggregate.blocked. Each blocked item needs escalation in the joint working room.

Answer (AR): انظر findings_aggregate.blocked. كل بند متعثر يحتاج تصعيد في غرفة العمل المشتركة.

### F-04 Which high-severity findings are still open?

ما الملاحظات عالية الخطورة ولا زالت مفتوحة؟

Answer (EN): List from findings_aggregate.top_blockers (or filter all findings where severity=high and status≠done).

Answer (AR): انظر القائمة في findings_aggregate.top_blockers (أو رشّح كل الملاحظات بـ severity=high و status≠done).

### F-05 Which distortion category has the most findings?

أي تصنيف للتشوه يحوي أكثر عدد من الملاحظات؟

Answer (EN): See findings_aggregate.by_category (largest entry).

Answer (AR): انظر findings_aggregate.by_category (أكبر إدخال).

### F-06 Which finding is closest to its deadline?

أي ملاحظة هي الأقرب لتاريخ موعدها المستهدف؟

Answer (EN): See findings_aggregate.top_blockers — the list is sorted by earliest target_date.

Answer (AR): انظر findings_aggregate.top_blockers — القائمة مرتبة بالأقرب موعداً.

### F-07 How many findings have been reopened more than once?

كم ملاحظة أُعيد فتحها أكثر من مرة؟

Answer (EN): Filter findings where reopenedCount > 1 — these indicate the same issue recurring (repeat-offender pattern).

Answer (AR): رشّح الملاحظات التي reopenedCount > 1 — هذه مؤشر على تكرار نفس المشكلة (نمط مخالف متكرر).

### F-08 What does ‘blocked’ status mean operationally?

ماذا يعني وصف ‘متعثرة’ تشغيلياً؟

Answer (EN): Work that cannot progress because of an external dependency (e.g., utility contractor not responding, owner notice unresolved, agency hand-off pending). These are the items the joint working room escalates first.

Answer (AR): أعمال لا يمكن تقدّمها بسبب اعتماد خارجي (مثل: مقاول مرافق غير مستجيب، إنذار مالك لم يُحل، انتقال صلاحيات بين الجهات معلق). هذه أولى البنود في غرفة العمل المشتركة للتصعيد.

## 5. Findings — by zone

الملاحظات — حسب النطاق

### Z-01 What is the situation in Zone 8?

ما الوضع في النطاق 8؟

Answer (EN): Phase 1, port stretch, high distortion density. Workshops belt with damaged median barriers and asphalt deterioration. Multiple agencies involved (JM, RGA, GDCD, Investment).

Answer (AR): المرحلة 1، قطاع الميناء، كثافة تشوه عالية. حزام ورش مع حواجز جزيرة وسطية متهالكة وتدهور سفلتة. عدة جهات مشاركة (JM, RGA, GDCD, Investment).

### Z-02 What is the situation in Zone 35?

ما الوضع في النطاق 35؟

Answer (EN): Phase 3, middle stretch, high distortion density. Slum cluster (~42 condemned dwellings), distorted ad-board cluster, fuel-station code violations. Owned mostly by HCM and the Investment partner.

Answer (AR): المرحلة 3، القطاع الأوسط، كثافة تشوه عالية. تجمع عشوائيات (~42 مسكن ملغى)، فوضى لوحات إعلانية، مخالفات محطات وقود. مملوك غالباً لـ HCM وشريك الاستثمار.

### Z-03 What is the situation in Zone 70?

ما الوضع في النطاق 70؟

Answer (EN): Phase 5, Haram approach, high distortion density. Prince Nayef Bridge perimeter restoration, inspection-point upgrade, barrier replacement. Highest leadership scrutiny before Hajj.

Answer (AR): المرحلة 5، مدخل الحرم، كثافة تشوه عالية. إعادة تأهيل حرم كبري الأمير نايف، تطوير نقطة التفتيش، استبدال الحواجز. أعلى تدقيق قيادي قبل الحج.

### Z-04 How many findings does Zone 8 have and how many are open?

كم عدد ملاحظات النطاق 8 وكم منها مفتوحة؟

Answer (EN): Use poc_zones[id=8].findings_total and findings_open.

Answer (AR): استخدم poc_zones[id=8].findings_total و findings_open.

### Z-05 Which PoC zone has the highest number of high-severity findings?

أي نطاق تجريبي يحوي أكثر ملاحظات عالية الخطورة؟

Answer (EN): Compare poc_zones[*].findings_high_severity.

Answer (AR): قارن poc_zones[*].findings_high_severity.

### Z-06 Are there bridges in any PoC zone?

هل توجد كباري في أي نطاق تجريبي؟

Answer (EN): Yes — Zone 70 contains Prince Nayef Bridge (approach). Asset type ‘bridge’ also appears in poc_zones[id=70].asset_count_by_type.

Answer (AR): نعم — النطاق 70 يحوي كبري الأمير نايف (المدخل). نوع الأصل ‘bridge’ يظهر أيضاً في poc_zones[id=70].asset_count_by_type.

### Z-07 What can you tell me about Zone 50?

ماذا يمكنك إخباري عن النطاق 50؟

Answer (EN): Zone 50 is in Phase 4 (Z46–Z60), middle sub-stretch. PoC data has not been injected for it yet — return the scope_notes.out_of_scope_response.

Answer (AR): النطاق 50 ضمن المرحلة 4 (Z46–Z60)، القطاع الأوسط. لم تُحقَن بيانات تجريبية له بعد — أعد الإجابة scope_notes.out_of_scope_response.

### Z-08 Which assets are in Zone 35?

ما الأصول الموجودة في النطاق 35؟

Answer (EN): Slum-area boundary, Service Plaza #4 (fuel station), and a planned median-landscaping strip. See poc_zones[id=35].asset_count_by_type.

Answer (AR): حدود منطقة عشوائيات، مجمع الخدمة رقم 4 (وقود)، وشريط تنسيق وسطي مخطط. انظر poc_zones[id=35].asset_count_by_type.

## 6. Contractors & governance

المقاولون والحوكمة

### A-01 Which contractors are involved on the MBS Road?

أي مقاولين يعملون على محور طريق الأمير محمد بن سلمان؟

Answer (EN): Ten in total: six government-internal entities (MoMAH — governance owner, HCM, JM, RGA, GDT, GDCD) and four private-sector vendors (Al-Rajhi Construction — ARC, Saudi Binladin Group — SBG, MA’AS Services — MAAS, and Tatweer Investment Partner — TIP).

Answer (AR): عشرة إجمالاً: ستة جهات حكومية داخلية (MoMAH — مالك الحوكمة، HCM، JM، RGA، GDT، GDCD) وأربعة مقاولين من القطاع الخاص (شركة الراجحي للإنشاءات — ARC، مجموعة بن لادن السعودية — SBG، ماس للخدمات — MAAS، وشريك تطوير الاستثمار — TIP).

### A-02 Which contractor owns the most findings overall?

أي مقاول يحمل أكبر عدد من الملاحظات؟

Answer (EN): Take the largest entry of findings_aggregate.by_contractor — currently TIP and MAAS share the lead with 5 each, followed by ARC at 4.

Answer (AR): انظر أكبر إدخال في findings_aggregate.by_contractor — حالياً TIP و MAAS يتشاركان الصدارة بـ 5 ملاحظات لكل منهما، يليهما ARC بـ 4.

### A-03 Which contractor has the most blocked items?

أي مقاول لديه أكثر بنود متعثرة؟

Answer (EN): Compare contractors[*].blocked_findings_count and take the max — currently RGA and HCM each have 1 blocked item open.

Answer (AR): قارن contractors[*].blocked_findings_count — حالياً RGA و HCM لدى كل منهما بند متعثر واحد مفتوح.

### A-04 Why does the report say governance is one of the four root causes?

لماذا يقول التقرير إن الحوكمة هي أحد الأسباب الجذرية الأربعة؟

Answer (EN): Because no single authority oversees the corridor end-to-end — 4 contractors involved in maintenance, 7 in infrastructure projects, 3 in studies, 4 in private-sector projects. Roles overlap and there is no joint operations room (slide 9).

Answer (AR): لأنه لا توجد جهة واحدة مشرفة على المحور كاملاً — 4 مقاولين في الصيانة، 7 في البنية التحتية، 3 في الدراسات، 4 في القطاع الخاص. تتداخل الأدوار ولا توجد غرفة عمليات مشتركة (شريحة 9).

### A-05 What is the proposed governance fix?

ما الحل الحوكمي المقترح؟

Answer (EN): An independent program led by MoMAH that joins HCM (Makkah) and Jeddah Municipality in a shared working room with mandates for findings remediation, vendor performance oversight, and stakeholder coordination.

Answer (AR): برنامج مستقل بقيادة MoMAH يجمع HCM (مكة) وأمانة جدة في غرفة عمل مشتركة بصلاحيات معالجة الملاحظات، ومتابعة أداء المقاولين، وتنسيق أصحاب المصلحة.

### A-06 Who is responsible for greenery and ad-board concessions?

من المسؤول عن التشجير وامتيازات اللوحات الإعلانية؟

Answer (EN): Tatweer Investment Partner (TIP) — a PPP vendor — under MoMAH oversight.

Answer (AR): شريك تطوير الاستثمار (TIP) — مقاول شراكة بين القطاعين العام والخاص — تحت إشراف MoMAH.

## 7. Vendor performance

أداء المقاولين

### V-01 Who is our best-performing vendor overall?

من هو أفضل مقاول من حيث الأداء بشكل عام؟

Answer (EN): Use vendor_performance.best_overall — based on a composite score that weights on-time delivery (40%), quality (30%), low fines (20%), and few late items (10%).

Answer (AR): انظر vendor_performance.best_overall — مبني على نتيجة مركبة تزن الالتزام بالمواعيد (40%)، الجودة (30%)، انخفاض الغرامات (20%)، وقلة البنود المتأخرة (10%).

### V-02 Which vendor has the most fines this year?

أي مقاول لديه أكبر مبلغ غرامات هذا العام؟

Answer (EN): Use vendor_performance.most_fined — Al-Rajhi Construction (ARC) leads at SAR 450,000 YTD, followed by Tatweer Investment Partner (TIP) at SAR 320,000.

Answer (AR): انظر vendor_performance.most_fined — شركة الراجحي للإنشاءات (ARC) في المقدمة بـ 450,000 ر.س منذ بداية العام، يليها شريك تطوير الاستثمار (TIP) بـ 320,000 ر.س.

### V-03 Which vendor is slipping on deadlines / has the most late findings?

أي مقاول متأخر عن المواعيد / لديه أكثر بنود متأخرة؟

Answer (EN): Use vendor_performance.most_late — Tatweer Investment Partner (TIP) currently has the most late findings (3), followed by RGA (3) and ARC (2).

Answer (AR): انظر vendor_performance.most_late — شريك تطوير الاستثمار (TIP) لديه أكثر بنود متأخرة (3)، يليه RGA (3) و ARC (2).

### V-04 Which vendor delivers the highest quality?

أي مقاول يقدم أعلى مستوى جودة؟

Answer (EN): Use vendor_performance.highest_quality — Saudi Binladin Group (SBG) leads with a quality score of 92/100. They are slower on deadlines but their bridge work meets the highest spec.

Answer (AR): انظر vendor_performance.highest_quality — مجموعة بن لادن السعودية (SBG) في المقدمة بنتيجة جودة 92/100. أبطأ في المواعيد لكن أعمال الكباري لديها وفق أعلى مواصفات.

### V-05 Who holds the largest contract on the corridor?

أي مقاول لديه أكبر قيمة عقد على المحور؟

Answer (EN): Use vendor_performance.largest_contract — Al-Rajhi Construction (ARC) at SAR 22.5M, followed by Tatweer Investment Partner (TIP) at SAR 18.9M and Saudi Binladin Group (SBG) at SAR 14.8M.

Answer (AR): انظر vendor_performance.largest_contract — شركة الراجحي للإنشاءات (ARC) بقيمة 22.5 مليون ر.س، يليها شريك تطوير الاستثمار (TIP) بـ 18.9 مليون ر.س، ثم مجموعة بن لادن السعودية (SBG) بـ 14.8 مليون ر.س.

### V-06 What is the total contract value committed on the corridor across all vendors?

ما إجمالي قيمة العقود الملتزم بها على المحور لدى جميع المقاولين؟

Answer (EN): Use vendor_performance.total_corridor_contract_value_sar.

Answer (AR): انظر vendor_performance.total_corridor_contract_value_sar.

### V-07 Show me the full vendor scorecard ranking.

أعرض بطاقة أداء كل المقاولين مرتبة.

Answer (EN): Use vendor_performance.ranked_by_composite — vendors sorted by composite score (best first). Each entry has the contractor’s id, acronym, and composite score (0..100).

Answer (AR): انظر vendor_performance.ranked_by_composite — مقاولون مرتبون حسب النتيجة المركبة (الأفضل أولاً). كل إدخال يحوي المعرّف والاختصار والنتيجة المركبة (0..100).

### V-08 Which vendor should we be most concerned about and why?

أي مقاول يجب أن نقلق منه أكثر ولماذا؟

Answer (EN): Tatweer Investment Partner (TIP) — lowest on-time rate among active vendors (52%), 3 late findings, SAR 320,000 in fines YTD, and 1 escalation. Combined with their large SAR 18.9M contract, this exposure warrants leadership attention. Action: schedule a contractor performance review and consider escalation in the joint working room.

Answer (AR): شريك تطوير الاستثمار (TIP) — أدنى نسبة التزام بالمواعيد بين المقاولين الفعّالين (52%)، 3 بنود متأخرة، 320,000 ر.س غرامات منذ بداية العام، وحالة تصعيد واحدة. مع حجم العقد الكبير (18.9 مليون ر.س)، هذه المخاطر تستحق اهتمام القيادة. الإجراء: جدولة مراجعة أداء المقاول ودراسة التصعيد في غرفة العمل المشتركة.

## 8. Budget

الميزانية

### B-01 How much development budget is committed in Zone 8?

كم حجم ميزانية التطوير الملتزم بها في النطاق 8؟

Answer (EN): See poc_zones[id=8].budget_committed_sar (SAR).

Answer (AR): انظر poc_zones[id=8].budget_committed_sar (ر.س).

### B-02 What share of the Zone 8 budget has been spent?

ما نسبة الإنفاق من ميزانية النطاق 8؟

Answer (EN): Compute poc_zones[id=8].budget_spent_sar / budget_committed_sar.

Answer (AR): احسب poc_zones[id=8].budget_spent_sar / budget_committed_sar.

### B-03 Which PoC zone has the largest committed budget?

أي نطاق تجريبي لديه أكبر ميزانية ملتزمة؟

Answer (EN): Compare poc_zones[*].budget_committed_sar.

Answer (AR): قارن poc_zones[*].budget_committed_sar.

### B-04 What is the total committed development budget across all PoC zones?

ما إجمالي ميزانية التطوير الملتزم بها لكل نطاقات التجربة؟

Answer (EN): Sum of poc_zones[*].budget_committed_sar.

Answer (AR): مجموع poc_zones[*].budget_committed_sar.

## 9. Hajj readiness

جاهزية الحج

### H-01 How many days until the next Hajj season?

كم يوماً متبقياً حتى موسم الحج القادم؟

Answer (EN): See hajj_readiness.days_remaining and hajj_readiness.next_hajj_date.

Answer (AR): انظر hajj_readiness.days_remaining و hajj_readiness.next_hajj_date.

### H-02 Are we on track for Hajj?

هل نحن ضمن المسار المخطط للحج؟

Answer (EN): Return hajj_readiness.summary_en / summary_ar — derived from average KPI progress vs target.

Answer (AR): أعد hajj_readiness.summary_en / summary_ar — مشتق من متوسط تقدّم المستهدفات.

### H-03 What short-term work must be done before Hajj?

ما الأعمال قصيرة المدى التي يجب إنجازها قبل الحج؟

Answer (EN): Per the report (slide 12): intensify contractor oversight, clear illegal workshops & yards, fix concrete barriers, improve appearance of inspection points along the corridor.

Answer (AR): حسب التقرير (شريحة 12): تكثيف الرقابة على المقاولين، إزالة الورش والمستودعات غير النظامية، إصلاح الحواجز الخرسانية، تحسين مظهر نقاط التفتيش على امتداد المحور.

### H-04 Which zone is the highest priority for Hajj readiness?

أي نطاق له أعلى أولوية لجاهزية الحج؟

Answer (EN): Zone 70 — Prince Nayef Bridge approach is the pilgrim entry; bridge perimeter and inspection-point appearance directly shape the welcome experience.

Answer (AR): النطاق 70 — مدخل كبري الأمير نايف هو مدخل الحجاج؛ حرم الكبري ومظهر نقطة التفتيش يحددان مباشرةً تجربة الترحيب.

## 10. Activity types

أنواع الأنشطة

### T-01 What is a ‘development activity’?

ما هو ‘النشاط التطويري’؟

Answer (EN): Major capital fixes from the report’s primary findings — e.g., new fuel station, demolish workshops, replace barriers, bridge restoration. Has a budget, contractor, target date.

Answer (AR): أعمال رأسمالية كبيرة من الملاحظات الأساسية في التقرير — مثل: محطة وقود جديدة، هدم ورش، استبدال حواجز، تأهيل كبري. لها ميزانية، مقاول، تاريخ مستهدف.

### T-02 What is an ‘operational activity’?

ما هو ‘النشاط التشغيلي’؟

Answer (EN): Day-to-day inspector findings — mostly visual-distortion items. Short cycle (Open → Assigned → Fixed → Verified). No major budget; has an inspector name and may have a reopen count.

Answer (AR): ملاحظات مفتشين يومية — معظمها تشوه بصري. دورة قصيرة (مفتوحة → مُسندة → مُصلحة → مُتحقق منها). بلا ميزانية كبيرة؛ لها اسم مفتش وقد يكون لها عدد مرات إعادة فتح.

### T-03 How many development vs operational items are tracked?

كم عدد البنود التطويرية مقابل التشغيلية؟

Answer (EN): See findings_aggregate.by_activity_type.

Answer (AR): انظر findings_aggregate.by_activity_type.

### T-04 When an operational finding keeps recurring (same workshop oil-spill 3rd time), what does that mean?

إذا تكررت ملاحظة تشغيلية (نفس ورشة تسرّب الزيت للمرة الثالثة)، ماذا يعني ذلك؟

Answer (EN): It is a ‘repeat-offender’ pattern. The reopenedCount metric flags it. These cases typically need escalation from operational handling to a development-style decision (e.g., demolition or licensing review).

Answer (AR): هذا نمط ‘مخالف متكرر’. مؤشّر reopenedCount يرصده. تحتاج هذه الحالات عادةً للتصعيد من المعالجة التشغيلية إلى قرار تطويري (مثل: هدم أو مراجعة ترخيص).

## 11. Scope & safety

النطاق والسلامة

### X-01 Can you answer questions about Riyadh roads or other cities?

هل تستطيع الإجابة عن طرق الرياض أو مدن أخرى؟

Answer (EN): No — this agent is scoped to the MBS Road corridor (Jeddah → Makkah) in the Makkah region. Anything outside that scope, decline politely and remind the user of the corridor.

Answer (AR): لا — هذا الوكيل محصور بمحور طريق الأمير محمد بن سلمان (جدة → مكة) في منطقة مكة المكرمة. أي طلب خارج هذا النطاق، اعتذر بأدب وذكّر المستخدم بنطاق المحور.

### X-02 Do you have data for zones outside Z8, Z35, Z70?

هل توجد بيانات لنطاقات خارج Z8 و Z35 و Z70؟

Answer (EN): Not yet. Return scope_notes.out_of_scope_response and offer the zone’s phase + sub-stretch if asked.

Answer (AR): ليس بعد. أعد scope_notes.out_of_scope_response واعرض المرحلة والقطاع الجغرافي إذا طُلب.

### X-03 Is the data in this PoC real?

هل البيانات في هذه التجربة حقيقية؟

Answer (EN): No — all findings, budgets, inspector names, and KPI percentages are synthetic, generated to demonstrate the platform. Real data will be loaded after sign-off.

Answer (AR): لا — جميع الملاحظات والميزانيات وأسماء المفتشين ونسب المستهدفات بيانات تجريبية أُنشئت لعرض المنصة. ستُحمَّل البيانات الحقيقية بعد الاعتماد.

→ Continue to 07 · Facts Snapshot (JSON)